## fp
A tracking system for beer warehouse inventory keeps track of what good are stored in a warehouse. As boxes of beer enter the warehouse, bar codes on the boxes that identify their contents are scanned and a record for each box is entered into a database of stored merchandise. As boxes leave the warehouse, their bar codes are scanned again by a different reader in order to remove them from the database. The bar code indicates the kind of beer and kind of container to be found in the box; a table of codes and meanings determines the correspondence between code and box contents. A user can query the inventory database for the presence or absence of particular kinds of boxes in the warehouse, Base upon the description calculate the function points of this project.

	Number	Multiplier	FP
Domain
External Input	2	3	6
External output	1	4	4
External Inquiries	1	2	3
Internal logical files	2	10	20
External Interface files	0	0	0
		UFP	33

Adjustments
Backup	5
specialized communication	1
distributed functions	1
existing op environment	2
online data entry	5
ILF updated online	5
adj points	14

FP	26.07

## Detailed COCOMO
				Example: / Consider a project to develop a full screen editor. The major components identified and their sizes are (i) Screen Edit – 4K (ii) Command Lang Interpreter – 2K (iii) File Input and Output – 1K (iv) Cursor movement – 2K (v) Screen Movement – 3K. Assume the Required software reliability is high, product complexity is high, analyst capability is high & programming language experience is low. / Size of modules : 4 + 2 + 1 + 2 + 3 = 13 KLOC [Organic]
Detailed COCOMO = Intermediate COCOMO + assessment of Cost Drivers impact on each phase. / Phases: / - Plans and requirements / - System Design / - Detailed Design / - Module code and test / I- ntegrate and test / Cost of each subsystem is estimated separately. This reduces the margin of error. / Procedure: / Multiply all 15 Cost Drivers to get Effort Adjustment Factor(EAF) / E(Effort) = ab(KLOC)^bb * EAF(in Person-Month) / D(Development Time) = cb(E)^db (in month) / Ep (Total Effort) = µp * E (in Person-Month) / Dp (Total Development Time) = τp * D (in month)

				Cost Drivers	Very Low	Low	Nominal	High	Very High	Extra High
				RELY	0.75	0.88	1	1.15	1.4	--
				CPLX	0.7	0.85	1	1.15	1.3	1.65
				ACAP	1.46	1.19	1	0.86	0.71
				LEXP	1.14	1.07	1	0.95	--	--

				EAF = 1.15 * 1.15 * 0.86 * 1.07 =				1.2169

				Initial Effort (E) = ab(KLOC)bb * EAF = 3.2*(12)1.05 * 1.2169 / = 52.9 person-months / Initial Development Time = cb(E)db =2.5*(52.9)0.38 = 11.29 months / Phase value of µp and τp

				Plan & Reqr	System Design	Detail Design	Module code & test	Integration & Test
				Organic Small µp	0.06	0.16	0.26	0.42	0.16
				Organic Small τp	0.1	0.19	0.24	0.39	0.18

				E	D	Ep (in person-months)	Dp (in months)
				Plan & Requirement	52.9	11.29	0.06*52.9 = 3.17	0.10*11.29=1.12
				System Design	52.9	11.29	0.16*52.9=8.46	0.19*11.29=2.14
				Detail Design	52.9	11.29	0.26*52.9=13.74	0.24*11.29=2.70
				Module code & test	52.9	11.29	0.42*52.9=22.21	0.39*11.29=4.40
				Integration & test	52.9	11.29	0.16*52.9=8.46	0.18*11.29=2.03

## COCOMO 2
				Example: Consider a database application project with the following characteristics: / The application has 4 screens with 4 views each and 7 data tables for 3 servers and 4 clients. / The application may generate two report of 6 sections each from 07 data tables for two server and 3 clients. There is 10% reuse of object points. / The developer’s experience and capability in the similar environment is low. The maturity of organization in terms of capability is also low. Calculate the object point count, New object points and effort to develop such a project.					Early design model: / Used in the early stages of a software project when very little may be known about: / -the size of the product to be developed, / -the nature of the target platform, / -the nature of the personnel to be involved in the project. / Uses Unadjusted Function Points (UFP) as the measure of size. / Based on a standard formula for COCOMO-II models: / PMnominal = A*(Size)^B / Where / PMnominal = Effort of the project in person months / A = Constant representing the nominal productivity, provisionally set to 2.5 / B = Scale factor / Size = Software size / The Scaling Factors that COCOMO-II model uses for the / calculation of B are: / Precedentness (PREC) / Development flexibility (FLEX) / Architecture/ Risk Resolution (RESL) / Team Cohesion (TEAM) / Process maturity (PMAT) / Early design cost drivers: / Product Reliability and Complexity (RCPX) / Required Reuse (RUSE) / Platform Difficulty (PDIF) / Personnel Capability (PERS) / Personnel Experience (PREX) / Facilities (FCIL) / Schedule (SCED)					Example: / A software project of application generator category with estimated 50 KLOC has to be developed. The scale factor (B) has low precedentness, high development flexibility and low team cohesion. / Other factors are nominal. The early design cost drivers like platform difficult (PDIF) and Personnel Capability (PERS) are high and others are nominal. / Calculate the Effort in person-months for the development of the project.					Post Architecture Model: / Most detailed model. / Used when a software life cycle architecture has been completed. / Used in the development and maintenance of software products in the application generators, system integration or infrastructure sectors. / Uses LOC, Fucntion points, and Cost drivers. / PM adjusted = PM nominal * (Sum of rating on scaling factors) / Cost drivers: / Product attributes: / Required Software Reliability (RELY) / Database Size (DATA) / Product Complexity (CPLX) / Documentation (DOCU) / Required Reusability (RUSE) / Computer attributes: / Execution Time Constraint (TIME) / Platform Volatility (PVOL) / Main Storage constraint (STOR) / Personnel attributes: / Analyst Capability (ACAP) / Personnel Continuity (PCON) / Programmer Experience (PEXP) / Programmer Capability (PCAP) / Analyst Experience(AEXP) / Language & Tool Experience (LTEX) / Project attributes: / Use of Software tools (TOOL) / Required development schedule (SCED) / Site Locations & Communications Technology b/w sites (SITE)					Example: / A software project of application generator category with estimated 50 KLOC has to be developed. / The scale factor (B) has low precedentness, high development flexibility and low team cohesion. / The identified 17 Cost drivers are high reliability (RELY), very high database size (DATA), high execution time constraint (TIME), very high analyst capability (ACAP), high programmers capability (PCAP). / The other cost drivers are nominal. / Calculate the effort in Person-Months for the development of the project. / Here B = 1.1129 / PMnominal = 194.41 Person-months / = 194.41 x (1.15 x 1.19 x 1.11 x 0.67 x 0.87) / = 194.41 x 0.885 / = 172.05 Person-months
COCOMO II stages: / Application Composition / Earlier Design / Post Architecture					Assess object counts: Estimate the number of screens, reports and 3 GL components that will comprise this application. / Classification of complexity levels: / We have to classify each object instance (depending on values of its characteristics) into :- / - simple / - medium / - difficult / Assign complexity weight to each object : / The weights are used for three object types : / - screen / - report / - 3GL components / Determine object points: Add all the weighted object instances to get one number and this known as object-point count. / Compute new object points: We have to estimate the percentage of reuse to be achieved in a project. Depending on the percentage reuse, the new object points (NOP) are computed. / Object Points * (100 - %reuse) / NOP = --------------------------------------------- / 100 / NOP are the object points that will need to be developed and differ from the object point count because there may be reuse( percentage of the Product development which is accomplished by exploiting the existence of existing component's design-or-development effort). / Calculation of productivity rate: The productivity rate can be calculated as: / Productivity rate (PROD) = NOP/Person month / Compute the effort in Persons-Months: When PROD is known, we may estimate effort in Person-Months as: / NOP / Effort in PM = ------------ / PROD					Schedule estimation: / Development time can be calculated using PMadjusted as a key factor and the desired equation is: / Where : / 0 constant, provisionally set to 3.67, B = Scaling factor / TDEVnominal = calendar time in months with a scheduled constraint / PMadjusted = Estimated effort in Person months (after adjustment) / Size measurement can be done in in KLOC or objects depending on the application model.

COCOMO procedure: / 1. Object count / 2. Classification of complexity levels / 3. Assign complexity weight / 4. Determine object points / 5. Compute new object points / 6. Calculation of productivity rate / 7. Computation of person/months

				Solution: / B = 0.91 + 0.01 * (Sum of rating on scaling factors for the project) / = 0.91 + 0.01 * (4.96 + 2.03 + 4.24 + 4.38 + 4.68) / = 0.91 + 0.01(20.29)=1.1129 / PMnominal = 2.5 * (50)1.1129 = 194.41 Person-months / The 7 cost drivers are: / PDIF = high (1.29) PERS = high (0.83) / RCPX = nominal (1.0) RUSE = nominal (1.0) / PREX = nominal (1.0) FCIL = nominal (1.0) / SCEO = nominal (1.0)

				No. Of Views	Total<4	Total<8	Total 8+
				Contained in a screen	(<2 servers	(2-3 servers	(>3 servers
				<3 clients)	3-5 clients)	>5 clients)
				<3	Simple	Simple	Medium
				3 to 7	Simple	Medium	Difficult
				>8	Medium	Difficult	Difficult

				No. Of Sections	Total<4	Total<8	Total 8+
				Contained in a report	(<2 servers	(2-3 servers	(>3 servers
				<3 clients)	3-5 clients)	>5 clients)
				0 or 1	Simple	Simple	Medium
				2 or 3	Simple	Medium	Difficult					Pm=	194.41* (1.29*0.83)
				4+	Medium	Difficult	Difficult					194.41 * 1.07
				208.115	person/months
				Object Type	Simple Complexity	Medium	Difficult Complexity

				Screen	1	2	3
				Report	2	5	8
				3GL	-	-	10
				Number of screens = 4 with 4 views each / Number of reports = 2 with 6 sections each / From Table we know that each screen will be of medium complexity and each report will be difficult complexity. / Using Table of complexity weights, we may calculate object point count / = 4 x 2 + 2 x 8 = 24

				For B computation:

				Scaling Factors	Very Low	Low	Nominal	High	Very High	Extra High
				Precedentness	6.2	4.96	3.72	2.48	1.24	0
				Development Flexibility	5.07	4.05	3.04	2.03	2.03	0
				Architecture/ Risk Resolution	7.07	5.65	4.24	2.83	1.41	0
				Team Cohesion	5.48	4.38	3.29	2.19	1.1	0
				Using the formula NOP is calculated as: / NOP= 24 * (100-10)/100=21.6 / Low value of productivity is given in above Productivity table = 7 / Efforts in PM=NOP/PROD=21.6/7=3.086 PM					Process Maturity	7.8	6.24	4.68	3.12	1.56	0
				Developer’s Experience And Capability	PROD (NOP/PM)
				Very low	4					If B=1.0, then Linear relationship b/w Effort & Size. / If B is different than 1.0, then Non-Linear relationship b/w Effort & Size. / If B<1.0, then the rate of increase of effort decreases as the size of the product increases. / If B>1.0, then the rate of increase of effort increases as the size of the product increases. / B = 0.91 + 0.01 * (Sum of rating on scaling factors for the project) / When all the scaling factors of a project are rated as extra high, / then the best value of B= 0.91 (for COCOMO II.2000) / when all the scaling factors of a project are rated as very low, / Then the worst value of B= 1.23 (for COCOMO II.2000) / Hence, the value of B may vary from 0.91 to 1.23
				Low	7
				Nominal	13
				High	25
				Very high	50

## Cost Drivers
Cost Drivers	Very Low	Low	Nominal	High	Very High	Extra High
RELY	0.75	0.88	1	2.48	1.24	0
DATA		0.93	1	2.03	2.03	0
CPLX	0.75	0.88	1	2.83	1.41	0
RUSE		0.91	1	2.19	1.1	0
DOCU	0.89	0.95	1	3.12	1.56	0
TIME			1	1.11	1.31	1.67
STOR			1	1.06	1.21	1.57
PVOL		0.87	1	1.15	1.3
ACAP	1.5	1.22	1	0.83	0.67
PCAP	1.37	1.16	1	0.87	0.74
PCON	1.24	1.1	1	0.92	0.84
AEXP	1.22	1.1	1	0.89	0.81
PEXP	1.25	1.12	1	0.88	0.81
LTEX	1.22	1.1	1	0.91	0.84
TOOL	1.24	1.12	1	0.86	0.72
SITE	1.25	1.1	1	0.92	0.84	0.78
SCED	1.29	1.1	1	1	1