## FP
Complexity point table
		Simple	Average	Complex
Inputs		2	4	6
Outputs		3	5	7					Data Communications
Files		5	10	15					Distributed Data Processing
Inquires		2	4	6					Performance Crucial	1
Interfaces		4	7	10					Heavily Used Configuration
					Transaction Rate	1
Example					Online Data Entry
Inputs			Weight	FP					End-User Efficiency	1
	Simple	1	2	2		cases				Online Update
	Average	0	4	0					Complex Processing
	Complex	0	6	0					Reusability
Outputs					cases				Installation Ease	1
	Average	1	5	5					Operational Ease	1
	Complex	0	7	0					Multiple sites	0
Files					table				Facilitate Change
	Complex	1	15	15					Project Adjustment Factor	5
Inquiries					user query
	Average	1	4	4
Interfaces					2				Adjustment calculation
	Average	2	7	14
	Complex	0	10	0					Adjustment FP = Unajusted FP x [0.65 +(adjustment factor X 0.01)]
					Adjusted FP =	28
				40	Unadjusted function points

Impact of fucntion points depend on organizations previous experience, for example:

By experience a programmer averages 18 funtion points per month
197 divided by 18
10.9444444444	man - months
Average programmer salary = 5200 per month
11 man-months x 5200 =
57200

## OP
Screens					Reports
	# sources of data tables					# sources of data tables
#Views	Total <4 / (<2 serves <3 clients)	Total < 8 / (2/3 servers 3-5 clients	Total 8+ / (>3 servers >5 clients		#of sections contained
<3	simple	simple	medium		0 or 1	simple	simple	medium
3 to 7	simple	medium	difficult		2 or 3	simple	medium	difficult
>8	medium	difficult	difficult		4+	medium	difficult	difficult

Weight					Productivity
Type	Simple	Medium	Difficult		Developer experience		Very low	low	nominal	high	very high
Screen	1	2	3		Productivity		4	7	13	25	50
Report	2	5	7		CASe		4	7	13	25	50
Modules / (3GL component)			10

Effort =	NOP /Productivity

NOP =	OP ((100-%reuse)/100)

Example

	Application will have 3 screens and will produce 1 report: – A booking screen: records a new sale booking – A pricing screen: shows the rate for each day and each flight – An availability screen: shows available flights – A sales report: shows total sale figures for the month and year, and compares figures with previous months and years / Booking screen: – Needs 3 data tables (customer info, customer history table, available seats) – Only 1 view of the screen is enough. So, the booking screen is classified as simple. ■ Similarly, the levels of difficulty of the pricing screen, the availability screen and the sales report are classified as simple, simple and medium, respectively. There is no 3GL component.

Name	Objects	Comp	Weight
Booking	Screen	Simple	1
Pricing	Screen	Simple	1
Availability	Screen	Medium	2
Sales	Report	Medium	5
		Total	9	OP

Developers experience		very LOW	4
CASE capability		LOW	7		Average	5.5
NOP	9

Effort	1.6363636364	man monthns

## COCOMO
	Basic

Effort(E) = ab * (KLOC)^bb(in Person-months) / DevelopmentTime(D) = cb * (E)^db (in month) / Average staff size(SS) = E/D (in Person) / Productivity(P) = KLOC / E (in KLOC/Person-month)

	Example
A project size of 200KLOC is to be developed.S/W development team has average experience on similar type of projects.The project schedule is not very tight.Calculate the effort and development time of the project. / Ans: 200 KLOC implies semi-detached mode. / Hence, E= 3.0 * (200)^1.12 = 1133.12 PM / D=2.5 * (1133.12)^0.35 = 29.3 M / Avg. staff size(SS) = E/D / = 1133.12/29.3=38.67 Persons. / Productivity (P) = KLOC/E / = 200/1133.12=0.1765 KLOC/PM.
						cocomo

						Size=	2		Calculations
						A=	2.4		E=	4.9692716344
						B=	1.05		D=	4.5976006846
						C=	2.5		SS=	1.080840198
						D=	0.38		P=	0.4024734704

	Intermediate

	Multiply all 15 Cost Drivers to get Effort Adjustment Factor(EAF) / E(Effort) = ab(KLOC)bb * EAF(in Person-Month) / D(Development Time) = cb(E)db (in month) / SS (Avg Staff Size) = E/D (in persons) / P (Productivity) = KLOC/E (in KLOC/Person-month)

	A new project with estimated 400 KLOC embedded system has to be developed. Project manager hires developers of low quality but a lot of experience in programming language. Calculate the Effort, Development time, Staff size & Productivity. / EAF = 1.29 * 0.95 = 1.22 / 400 KLOC implies Embedded System / Effort = 3.6*(400)^1.20 * 1.22 = 4772.81 * 1.22 = 5822.83 person-months / Development Time = 2.5 * (5822.83)^0.32 = 40.06 months / Avg. Staff Size = E/D = 5822.83/40.06 = 145.35 persons / Productivity = KLOC/Effort = 400/5822.83 = 0.068 KLOC/person-month